## Backlog
ID | Level | Parent | Title | Team | Epic | Sprint | Days | Done when | Model link | Status | Marks | Iteration | Assignee | Spent (d) | GitLab
T1 | Tome |  | Stand up MBSE DevSecOps | [6 empty] | OPEN
E1 | Epic | T1 | GitLab project and gitflow | [6 empty] | OPEN
S1-project | Story | E1 | Create the GitLab group and model project | MBSE | E1 | 1 | 3 | The project exists with the settings in project.conf; A direct push to develop is refused; CODEOWNERS and the issue and MR templates are on develop | area::pipeline | DONE |  |  | tom
S1-project.K1 | Task | S1-project | Apply project.conf with gitlab.pl setup; request the runner | MBSE | E1 |  | 1 |  |  | DONE |  |  | tom
S1-project.K2 | Task | S1-project | Prove a direct push to develop is refused | MBSE | E1 |  | 1 |  |  | DONE |  |  | tom
S1-project.K3 | Task | S1-project | Commit CODEOWNERS, the templates and .gitignore | MBSE | E1 |  | 1 |  |  | DONE |  |  | tom
S2-enablers | Story | E1 | Enablers, decisions and conventions on record | MBSE | E1 | 2 | 4.5 | The request for enablers is with the PM; docs/adr holds D-1 to D-10; docs/conventions and docs/onboarding are in the repo | area::pipeline | DONE |  |  | jim
S2-enablers.K1 | Task | S2-enablers | Memo: request for enablers | MBSE | E1 |  | 1 |  |  | DONE |  |  | jim
S2-enablers.K2 | Task | S2-enablers | Write docs/adr/0001..0010 | MBSE | E1 |  | 1.5 |  |  | DONE |  |  | jim
S2-enablers.K3 | Task | S2-enablers | Conventions and onboarding docs into docs/ | MBSE | E1 |  | 1 |  |  | DONE |  |  | jim
S2-enablers.K4 | Task | S2-enablers | Toolchain security kickoff with the ISSM | MBSE | E1 |  | 1 |  |  | DONE |  |  | jim
S5-rehearse | Story | E1 | Release rehearsal and a spillage tabletop | MBSE | E1 | 5 | 3 | A release and a hotfix went through a sandbox project; The spillage tabletop is written up | area::pipeline | DONE |  |  | tom
S5-rehearse.K1 | Task | S5-rehearse | Rehearse release and hotfix in tidewater/sandbox | MBSE | E1 |  | 2 |  |  | DONE |  |  | tom
S5-rehearse.K2 | Task | S5-rehearse | Spillage tabletop: a marked file pushed by mistake | MBSE | E1 |  | 1 |  |  | DONE |  |  | tom
S6-baseline | Story | E1 | Interim baseline-0 for the program review | MBSE | E1 | 6 | 2 | baseline-0 is tagged on main and rebuilds identically; The CCB concurred on the release MR; The release notes are published | area::pipeline | OPEN |  |  | tom
S6-baseline.K1 | Task | S6-baseline | Release branch, CCB concurrence, tag baseline-0, back-merge | MBSE | E1 |  | 2 |  |  | OPEN |  |  | tom
E2 | Epic | T1 | Pipeline and quality gates | [6 empty] | OPEN
S1-pipeline | Story | E2 | Draft the first pipeline and run it locally | MBSE | E2 | 1 | 1.5 | The draft runs grammar, lint and outline on drop 1 with gitlab.pl ci | area::pipeline | DONE |  |  | tom
S1-pipeline.K1 | Task | S1-pipeline | Draft .gitlab-ci.yml: grammar, lint, outline | MBSE | E2 |  | 0.5 |  |  | DONE |  |  | tom
S1-pipeline.K2 | Task | S1-pipeline | Run the draft locally on drop 1 with gitlab.pl ci | MBSE | E2 |  | 1 |  |  | DONE |  |  | tom
S2-runner | Story | E2 | Runner online; the first pipeline gates every MR | MBSE | E2 | 2 | 3 | A pipeline runs on every MR; "Pipelines must succeed" is on; JUnit and Code Quality reports show on the MR | area::pipeline | DONE |  |  | tom
S2-runner.K1 | Task | S2-runner | Check the runner registration and tags | MBSE | E2 |  | 0.5 |  |  | DONE |  |  | tom
S2-runner.K2 | Task | S2-runner | Commit the pipeline; fix it for the PowerShell runner with ci/job.pl | MBSE | E2 |  | 2 |  |  | DONE |  |  | tom
S2-runner.K3 | Task | S2-runner | Turn on "pipelines must succeed" and the MR report widgets | MBSE | E2 |  | 0.5 |  |  | DONE |  |  | tom
S2-todo-docs | Story | E2 | TODO burn-down and generated docs in the pipeline | MBSE | E2 | 2 | 2 | The todo job counts TODO lines on every MR; docs/ is generated and the docs job keeps it current | area::pipeline | DONE |  |  | tom
S2-todo-docs.K1 | Task | S2-todo-docs | Add the todo and docs jobs; commit docs/ | MBSE | E2 |  | 2 |  |  | DONE |  |  | tom
S3-trace | Story | E2 | Trace report and secret detection in the pipeline | MBSE | E2 | 3 | 2.5 | The trace job reports C/F/G/I and drift; The secrets job runs on every MR | area::pipeline | DONE |  |  | tom
S3-trace.K1 | Task | S3-trace | Add the trace job (report only) and the secrets job | MBSE | E2 |  | 2.5 |  |  | DONE |  |  | tom
S4-pages | Story | E2 | The model site on GitLab Pages, rebuilt nightly | MBSE | E2 | 4 | 3 | The pages job publishes the site on every merge to develop; A nightly schedule rebuilds it | area::pipeline | DONE |  |  | tom
S4-pages.K1 | Task | S4-pages | Add the pages job and the nightly schedule | MBSE | E2 |  | 3 |  |  | DONE |  |  | tom
S5-ratchet | Story | E2 | The trace job becomes a gate | MBSE | E2 | 5 | 2 | The trace job fails an MR that adds an orphan, an unverified requirement or drift | area::pipeline | DONE |  |  | tom
S5-ratchet.K1 | Task | S5-ratchet | Trace ratchet: fail only on new gaps | MBSE | E2 |  | 2 |  |  | DONE |  |  | tom
E3 | Epic | T1 | Team practices and onboarding | [6 empty] | OPEN
S1-learn | Story | E3 | Learn the tools: survival kit, git, Vim, the operating model | MBSE | E3 | 1 | 4 | Each of us finished practice lessons 10 and 11; Each of us read the primer's Part II chapters for our role | area::pipeline | DONE |  |  | jim
S1-learn.K1 | Task | S1-learn | Practice lessons 10-11; the operating model chapter | MBSE | E3 |  | 1 |  |  | DONE |  |  | jim
S1-learn.K2 | Task | S1-learn | Practice lessons 10-11; the survival kit, git and Vim chapters | MBSE | E3 |  | 1.5 |  |  | DONE |  |  | bob
S1-learn.K3 | Task | S1-learn | Practice lessons 10-11; the survival kit, git and Vim chapters | MBSE | E3 |  | 1.5 |  |  | DONE |  |  | tom
S1-laptops | Story | E3 | Laptops ready: Git for Windows, Vim, the kit | MBSE | E3 | 1 | 3 | kickoff.pl doctor passes on all three laptops | area::pipeline | DONE |  |  | tom
S1-laptops.K1 | Task | S1-laptops | Set up Jim's laptop; kickoff.pl doctor | MBSE | E3 |  | 1 |  |  | DONE |  |  | jim
S1-laptops.K2 | Task | S1-laptops | Set up Bob's laptop; kickoff.pl doctor | MBSE | E3 |  | 1 |  |  | DONE |  |  | bob
S1-laptops.K3 | Task | S1-laptops | Set up Tom's laptop; kickoff.pl doctor | MBSE | E3 |  | 1 |  |  | DONE |  |  | tom
S1-agree | Story | E3 | Working agreements: Definition of Ready and Done | MBSE | E3 | 1 | 0.5 | Definition of Ready and Definition of Done on the wiki | area::pipeline | DONE |  |  | jim
S1-agree.K1 | Task | S1-agree | Write the Definition of Ready and Done in the wiki | MBSE | E3 |  | 0.5 |  |  | DONE |  |  | jim
S2-learn | Story | E3 | Learn: practice lessons 12-13, Vim for models, the SysML v2 workbook (first half) | MBSE | E3 | 2 | 3 | Lessons 12-13 done by all three; The workbook's first half done by Bob and Tom | area::pipeline | DONE |  |  | bob
S2-learn.K1 | Task | S2-learn | Practice lessons 12-13; the diagrams chapter | MBSE | E3 |  | 0.5 |  |  | DONE |  |  | jim
S2-learn.K2 | Task | S2-learn | Lessons 12-13; Vim for models; workbook first half | MBSE | E3 |  | 1.5 |  |  | DONE |  |  | bob
S2-learn.K3 | Task | S2-learn | Lessons 12-13; Vim for models; workbook first half | MBSE | E3 |  | 1 |  |  | DONE |  |  | tom
S2-demo | Story | E3 | Sprint 2 demo: the pipeline and the drop on develop | MBSE | E3 | 2 | 0.5 | The demo is given | area::pipeline | DONE |  |  | tom
S2-demo.K1 | Task | S2-demo | Prepare and give the sprint 2 demo | MBSE | E3 |  | 0.5 |  |  | DONE |  |  | tom
S3-learn | Story | E3 | Learn: the workbook second half; talking about progress | MBSE | E3 | 3 | 2.5 | Everyone drafts the stand-up with talk.pl; The Day-9 rehearsal held | area::pipeline | DONE |  |  | tom
S3-learn.K1 | Task | S3-learn | talk.pl: draft, then edit, the stand-up | MBSE | E3 |  | 0.5 |  |  | DONE |  |  | jim
S3-learn.K2 | Task | S3-learn | Workbook second half; talk.pl | MBSE | E3 |  | 1 |  |  | DONE |  |  | bob
S3-learn.K3 | Task | S3-learn | talk.pl; the Day-9 demo rehearsal | MBSE | E3 |  | 1 |  |  | DONE |  |  | tom
S4-learn | Story | E3 | Learn: reviewing a model change; the rehearsed demo | MBSE | E3 | 4 | 1.5 | Each reviewer has reviewed with line comments; The Day-9 rehearsal held | area::pipeline | DONE |  |  | bob
S4-learn.K1 | Task | S4-learn | Reviewing a model change: the checklist | MBSE | E3 |  | 0.5 |  |  | DONE |  |  | jim
S4-learn.K2 | Task | S4-learn | Reviewing a model change: line comments | MBSE | E3 |  | 0.5 |  |  | DONE |  |  | bob
S4-learn.K3 | Task | S4-learn | The Day-9 demo rehearsal | MBSE | E3 |  | 0.5 |  |  | DONE |  |  | tom
S4-review | Story | E3 | First sprint review with the program office; the delivery interface with the prime | MBSE | E3 | 4 | 1.5 | The program office has seen the site; The pipeline ICD meeting held | area::pipeline | DONE |  |  | jim
S4-review.K1 | Task | S4-review | Sprint review with the program office | MBSE | E3 |  | 1 |  |  | DONE |  |  | jim
S4-review.K2 | Task | S4-review | Agree the delivery interface with the prime (meeting) | MBSE | E3 |  | 0.5 |  |  | DONE |  |  | jim
S5-learn | Story | E3 | Learn: the requirement recipe; writing memos from the model | MBSE | E3 | 5 | 1 | The recipe chapter read; one memo drafted from pipeline numbers | area::requirements | DONE |  |  | jim
S5-learn.K1 | Task | S5-learn | The recipe chapter; a memo from pipeline numbers | MBSE | E3 |  | 0.5 |  |  | DONE |  |  | jim
S5-learn.K2 | Task | S5-learn | The recipe chapter | MBSE | E3 |  | 0.5 |  |  | DONE |  |  | bob
S6-learn | Story | E3 | Learn: memos and briefings from the model | MBSE | E3 | 6 | 0.5 | The memo chapter read before the briefing | area::pipeline | OPEN |  |  | jim
S6-learn.K1 | Task | S6-learn | The memo and briefing chapters | MBSE | E3 |  | 0.5 |  |  | OPEN |  |  | jim
S6-briefing | Story | E3 | Retrospective, the management briefing and the plan for next semester | MBSE | E3 | 6 | 2 | The briefing and the memo are delivered; The next semester's epics are ready | area::pipeline | OPEN |  |  | jim
S6-briefing.K1 | Task | S6-briefing | The twelve-week briefing and memo | MBSE | E3 |  | 2 |  |  | OPEN |  |  | jim
E4 | Epic | T1 | Toolchain security and authorization to use | [6 empty] | OPEN
S3-runner | Story | E4 | Runner hardening with the ISSM | MBSE | E4 | 3 | 2 | The runner service account is approved; The hardening checklist is in the wiki | area::pipeline | DONE |  |  | tom
S3-runner.K1 | Task | S3-runner | Runner service account and hardening checklist | MBSE | E4 |  | 2 |  |  | DONE |  |  | tom
T2 | Tome |  | Port Tidewater v1 to SysML v2 | [6 empty] | OPEN
E5 | Epic | T2 | Drop 1 intake and first import | [6 empty] | OPEN
S1-receive | Story | E5 | Receive drop 1 and record it | MBSE | E5 | 1 | 1.5 | Every file matches its MANIFEST sha256; The Prime Drop issue holds the checklist | area::requirements | DONE |  |  | jim
S1-receive.K1 | Task | S1-receive | Log the CDRL delivery and check the sha256 of every file | MBSE | E5 |  | 1 |  |  | DONE |  |  | jim
S1-receive.K2 | Task | S1-receive | Open the Prime Drop issue with its checklist | MBSE | E5 |  | 0.5 |  |  | DONE |  |  | jim
S1-assess | Story | E5 | Convert drop 1 and assess it | MBSE | E5 | 1 | 3 | Both converter reports are attached; The TODO inventory by package is on the wiki; The port backlog has estimates | area::requirements | DONE |  |  | bob
S1-assess.K1 | Task | S1-assess | Run both converters with --report on drop 1 | MBSE | E5 |  | 1 |  |  | DONE |  |  | bob
S1-assess.K2 | Task | S1-assess | Write the TODO inventory by package | MBSE | E5 |  | 1 |  |  | DONE |  |  | bob
S1-assess.K3 | Task | S1-assess | Estimate the port backlog with the team | MBSE | E5 |  | 1 |  |  | DONE |  |  | bob
S2-import | Story | E5 | Import drop 1 through the vendor branch, in layers | MBSE | E5 | 2 | 4 | The layout map is decided and committed; vendor/prime holds the converter output of drop 1; The merge MR is on develop, outline count recorded | area::requirements | DONE |  |  | bob
S2-import.K1 | Task | S2-import | Decide the layered layout; the layout map | MBSE | E5 |  | 1 |  |  | DONE |  |  | bob
S2-import.K2 | Task | S2-import | Import drop 1 onto vendor/prime | MBSE | E5 |  | 1 |  |  | DONE |  |  | tom
S2-import.K3 | Task | S2-import | Review and merge the drop-1 MR; record the outline count | MBSE | E5 |  | 2 |  |  | DONE |  |  | bob
E6 | Epic | T2 | Structure: close the structure TODOs | [6 empty] | OPEN
S2-conventions | Story | E6 | Level conventions for the part tree | MBSE | E6 | 2 | 2 | model/library/conventions/Conventions.sysml defines L1Network..L6Component and Procured; sysml.conf names the level tags | area::gov | DONE |  |  | bob
S2-conventions.K1 | Task | S2-conventions | Write the conventions package | MBSE | E6 |  | 1.5 |  |  | DONE |  |  | bob
S2-conventions.K2 | Task | S2-conventions | Name the level tags in sysml.conf | MBSE | E6 |  | 0.5 |  |  | DONE |  |  | bob
S3-network | Story | E6 | Close the Network TODO lines | MBSE | E6 | 3 | 3 | No TODO lines in Network.sysml; The pipeline is green | area::network | DONE |  |  | bob
S3-network.K1 | Task | S3-network | Level tags in Network | MBSE | E6 |  | 1 |  |  | DONE |  |  | bob
S3-network.K2 | Task | S3-network | The include use case in ReviewObservations | MBSE | E6 |  | 2 |  |  | DONE |  |  | bob
S4-stations | Story | E6 | Close the Stations level tags | MBSE | E6 | 4 | 5 | No level-stereotype TODO lines in Stations.sysml | area::stations | DONE |  |  | bob
S4-stations.K1 | Task | S4-stations | Level tags in Stations | MBSE | E6 |  | 3 |  |  | DONE |  |  | bob
S4-stations.K2 | Task | S4-stations | Walk the Stations tree with the prime's modeler; record what they confirmed | MBSE | E6 |  | 2 |  |  | DONE |  |  | bob
S4-types | Story | E6 | Units and value types | MBSE | E6 | 4 | 2 | No TODO lines in Types.sysml | area::types | DONE |  |  | bob
S4-types.K1 | Task | S4-types | Value types specialize ISQ quantities | MBSE | E6 |  | 2 |  |  | DONE |  |  | bob
S4-cycle-no | Story | E6 | Break the Network <-> Operations cycle | MBSE | E6 | 4 | 2 | One cycle fewer in the package view; A DR asks the prime to drop the dependency | area::network | DONE |  |  | tom
S4-cycle-no.K1 | Task | S4-cycle-no | Remove the ServiceVessel -> Technician dependency | MBSE | E6 |  | 2 |  |  | DONE |  |  | tom
S5-procured | Story | E6 | Procured parts as metadata; DataCenter level tags | MBSE | E6 | 5 | 3.5 | Procured parts carry @Procured; No level-stereotype TODO lines in DataCenter.sysml | area::stations | DONE |  |  | bob
S5-procured.K1 | Task | S5-procured | Procured parts as metadata | MBSE | E6 |  | 2 |  |  | DONE |  |  | bob
S5-procured.K2 | Task | S5-procured | Level tags in DataCenter | MBSE | E6 |  | 1.5 |  |  | DONE |  |  | bob
S5-legacy | Story | E6 | Untangle the Legacy Import package | MBSE | E6 | 5 | 3 | model/legacy/Legacy_Import.sysml is gone from develop; A DR asks the prime to delete it upstream | area::legacy | DONE |  |  | tom
S5-legacy.K1 | Task | S5-legacy | Remove the Legacy Import package from the v2 model | MBSE | E6 |  | 2 |  |  | DONE |  |  | tom
S5-legacy.K2 | Task | S5-legacy | DR-5: ask the prime to delete Legacy Import | MBSE | E6 |  | 1 |  |  | DONE |  |  | jim
S6-operations | Story | E6 | Level tags in Operations | MBSE | E6 | 6 | 1.5 | No level-stereotype TODO lines left in model/physical | area::operations | OPEN |  |  | tom
S6-operations.K1 | Task | S6-operations | Level tags in Operations | MBSE | E6 |  | 1.5 |  |  | OPEN |  |  | tom
E7 | Epic | T2 | Requirements and trace | [6 empty] | OPEN
S3-doors | Story | E7 | DOORS modules into the model | MBSE | E7 | 3 | 3 | model/requirements holds the three DOORS modules; The trace report runs on every change | area::requirements | DONE |  |  | jim
S3-doors.K1 | Task | S3-doors | Re-import drop 1 with the DOORS modules on vendor/prime | MBSE | E7 |  | 2 |  |  | DONE |  |  | jim
S3-doors.K2 | Task | S3-doors | Merge the DOORS modules to develop | MBSE | E7 |  | 1 |  |  | DONE |  |  | bob
S3-drift | Story | E7 | First drift and gap analysis from the trace | MBSE | E7 | 3 | 2 | Each gap in the trace report has a finding written up | area::requirements | DONE |  |  | jim
S3-drift.K1 | Task | S3-drift | Write up the drift and the trace gaps | MBSE | E7 |  | 2 |  |  | DONE |  |  | jim
S4-dr | Story | E7 | Discrepancy reports DR-1 to DR-4 to the prime | MBSE | E7 | 4 | 2 | DR-1 to DR-4 are open, owner::prime, sent through the contract channel | area::requirements | DONE |  |  | jim
S4-dr.K1 | Task | S4-dr | Open DR-1 to DR-4 | MBSE | E7 |  | 2 |  |  | DONE |  |  | jim
S5-spaghetti | Story | E7 | Prune ObservingStation's trace spaghetti | MBSE | E7 | 5 | 2 | The duplicate traces are gone; The trace job shows no new gap | area::stations | DONE |  |  | bob
S5-spaghetti.K1 | Task | S5-spaghetti | Remove the duplicate trace links | MBSE | E7 |  | 2 |  |  | DONE |  |  | bob
S5-recipe | Story | E7 | Grade our requirements with the recipe | MBSE | E7 | 5 | 2 | The recipe report runs on every MR; Findings on DOORS text are a DR to the prime | area::requirements | DONE |  |  | jim
S5-recipe.K1 | Task | S5-recipe | Read the recipe findings for the DOORS modules | MBSE | E7 |  | 1 |  |  | DONE |  |  | jim
S5-recipe.K2 | Task | S5-recipe | DR-6: weak verbs and missing parts in the DOORS text | MBSE | E7 |  | 1 |  |  | DONE |  |  | jim
S6-vcrm | Story | E7 | VCRM: which requirements are verified, and how | MBSE | E7 | 6 | 2 | The vcrm job publishes the VCRM on the site; Jim's inspection verdicts are in verification/results-gov.csv | area::verification | OPEN |  |  | jim
S6-vcrm.K1 | Task | S6-vcrm | Add the vcrm job | MBSE | E7 |  | 1 |  |  | OPEN |  |  | tom
S6-vcrm.K2 | Task | S6-vcrm | Enter and sign the inspection verdicts | MBSE | E7 |  | 1 |  |  | OPEN |  |  | jim
E8 | Epic | T2 | Behavior and analysis | [6 empty] | OPEN
S6-buoymodes | Story | E8 | BuoyModes state machine by hand | MBSE | E8 | 6 | 3 | The BuoyModes TODO is replaced by an exhibit state; GovBehavior holds the state def | area::behavior | OPEN |  |  | bob
S6-buoymodes.K1 | Task | S6-buoymodes | Write the BuoyModes state def; exhibit it on MooredBuoy | MBSE | E8 |  | 3 |  |  | OPEN |  |  | bob
S6-flows | Story | E8 | Fork, pin and object flow in ObserveCoast | MBSE | E8 | 6 | 1 | No TODO lines in Behavior.sysml | area::behavior | OPEN |  |  | bob
S6-flows.K1 | Task | S6-flows | Fork, pin, object and control flow by hand | MBSE | E8 |  | 1 |  |  | OPEN |  |  | bob
S6-exchange | Story | E8 | Data exchange table for the program review | MBSE | E8 | 6 | 2 | docs/data-exchange.md is generated from the interface items and flow properties; It is shown at the briefing | area::interfaces | OPEN |  |  | tom
S6-exchange.K1 | Task | S6-exchange | Document the flow properties in Interfaces | MBSE | E8 |  | 1 |  |  | OPEN |  |  | tom
S6-exchange.K2 | Task | S6-exchange | Generate the data exchange table | MBSE | E8 |  | 1 |  |  | OPEN |  |  | tom
E9 | Epic | T2 | Drops 2 and 3 during the port | [6 empty] | TODO
E10 | Epic | T2 | Baseline 1 and acceptance | [6 empty] | TODO
T3 | Tome |  | Maintain against prime drops | [6 empty] | TODO
E11 | Epic | T3 | Drop intake automation | [6 empty] | TODO
E12 | Epic | T3 | Drops 4 and 5 | [6 empty] | TODO
E13 | Epic | T3 | Drops 6 and 7 | [6 empty] | TODO
E14 | Epic | T3 | Sustainment operations | [6 empty] | TODO
E15 | Epic | T3 | Engineering with the model | [6 empty] | TODO
E16 | Epic | T3 | Security engineered into Tidewater | [6 empty] | TODO