## Start
Agile kit -- Excel edition
Yellow cells are yours to type in. Everything else is a formula over the Items and Log tables. No macros.
Settings
Sprint 1 starts | 2026-09-23
Sprint length (calendar days) | 14
As of (blank = today) | 2026-10-06
Points unit | SP
Project | demo
Stand-up date (blank = as of) | 2026-10-05
Now
Current sprint
Sprint starts
Sprint ends
Working day of sprint
As of
Thresholds (WORKFLOW section 6)
Blocked: amber after (days) | 3
Blocked: red after (days) | 5
Team load: high | 110%
Team load: low | 70%
Progress by working day 8 | 60%
Predictability: at least | 80%
Carryover: at most | 20%
Punt rate: at most | 20%
On-time delivery: at least | 80%
Same person, share of team points (bus factor) | 40%
Backlog age: flag after (days) | 90
Verbs (the Log table's third column)
Verb | Arg | State after | Meaning
commit | sprint N (blank = the sprint of the date) | OPEN | into a sprint at planning
carry | sprint N | OPEN | not done at sprint end: into the next sprint
done |  | DONE | finished, meets the Definition of Done
block |  |  | blocked from outside the team: why in Note (shows as WAIT)
unblock |  |  | the blocker is gone
hold |  | HOLD | interrupted by higher-priority work: why in Note
resume |  | OPEN | back from hold
punt |  | TODO | too hard as written: back to the team backlog, why in Note
redo | sprint N | OPEN | the demo found it wrong: back into a sprint
pass | team | TODO | another team should do it: into their backlog
drop |  | DROP | should not be done
est | points |  | re-estimate: the new size
sync | other ID |  | coordinated across teams (a note)
note |  |  | anything worth keeping
Every day
1. Townhall: copy the Teams meeting chat (Ctrl+A, Ctrl+C in the chat) and paste it into Standup!A6.
2. Lint: read the flags, copy the Reply column back into the chat, copy suggested rows (Date..Note) into the Log.
3. Log: type what happened -- one row per verb (done, block, hold, punt ...). Never edit old rows; add new ones.
4. Look: Quad (the weekly page), Health (thresholds), Teams, Burndown, Velocity. File > Print or paste into Outlook.
5. Dashboard: open agile-dashboard.html in Edge and load this file for charts you can copy into mail or slides.
Sprint planning: add Items, then a commit row per task. Sprint end: a carry row for each unfinished task.
The Items and Log tables grow when you type on the row just below them. Keep column order; add columns to the right.

## Quad
Sprint progress |  |  |  | On-time delivery
Technical priorities (this sprint) |  |  |  | Watch items (blocked, held, unassigned)
ID | State | Title | Owner | ID | State | Why | Days
30 / 60 / 90 milestones |  |  |  | Accomplishments (done in the last 7 days)
Epic | Status | Due | Pct done | ID | Done on | Title | Owner
Punted, last 4 sprints |  |  |  | Blocked > 3 days

## Health
Health: every metric against its threshold
RED and AMBER need an action; the action is in the last column (WORKFLOW section 6).
Metric | Value | Level | Action
Blocked past the red line (tasks) |  |  | Escalate to the PM today; name an owner for the outside dependency.
Blocked past the amber line (tasks) |  |  | Raise at the townhall; swarm or re-plan.
Teams over capacity |  |  | Move work out at the next refinement.
Teams under capacity |  |  | Pull ready work from the backlog.
Sprint progress (from working day 8) |  |  | Cut scope with the teams now, not on day 14.
Unassigned tasks in the sprint |  |  | Every committed task has one owner.
Predictability, last finished sprint |  |  | Commit to the 3-sprint velocity, not the hope.
Carryover, last finished sprint |  |  | Smaller tasks; split at refinement.
Punt rate, last finished sprint |  |  | The Definition of Ready is not holding: rewrite before planning.
Epics late or at risk |  |  | Re-plan the epic or move its target with the sponsor.
People over the bus-factor share |  |  | Pair or hand over; one person should not hold the team.
Backlog tasks older than the age limit |  |  | Refine or drop old backlog.
Silent at the last stand-up (people) |  |  | A 1:1 message; three days running is a conversation.
Log rows that do not check |  |  | Fix the ID or verb in the Log (Check column).

## Standup
Stand-up: paste the Teams chat into A6 (Ctrl+V). One line per row; Y: / T: / B: lines under each name.
Date
Names come from the Roster. "[8:31 AM] Ann Lee", "Ann Lee (08:31)" and "Ann Lee" on its own line all start a person.
Chat (paste here) | Name | Speaker | Tag | Text
Meeting started
[8:31 AM] Ann Contracting
Y: pairing on the carryover
T: code review
B: none
[8:32 AM] Bob Contracting
Y: pairing on the carryover
T: code review
B: none
[8:33 AM] Cy Contracting
Y: finished IF-31, merged
T: code review
B: none
[8:34 AM] Dee Contracting
Y: pairing on the carryover
T: code review
B: none
[8:35 AM] Eve Contracting
Y: pairing on the carryover
T: code review
B: none
[8:36 AM] Fay Contracting
Y: pairing on the carryover
T: code review
B: none
[8:37 AM] Gus Executive
Y: pairing on the carryover
T: code review
B: none
[8:38 AM] Hal Executive
Y: pairing on the carryover
T: code review
B: none
[8:39 AM] Ida Executive
Y: worked on IF-22
T: continue IF-22
B: none
[8:40 AM] Jon Executive
Y: pairing on the carryover
T: code review
B: none
[8:41 AM] Kim Executive
Y: finished E-221, merged
T: continue IF-24
B: none
[8:42 AM] Lou Executive
Y: pairing on the carryover
T: code review
B: none
[8:43 AM] Max Finance
Y: worked on IF-10
T: continue IF-10
B: none
[8:44 AM] Nia Finance
Y: pairing on the carryover
T: code review
B: none
[8:45 AM] Ola Finance
Y: pairing on the carryover
T: code review
B: none
[8:46 AM] Pat Finance
Y: pairing on the carryover
T: code review
B: none
[8:47 AM] Quinn Finance
Y: pairing on the carryover
T: code review
B: none
[8:48 AM] Ray Finance
Y: pairing on the carryover
T: code review
B: none
[8:49 AM] Sam HR
Y: finished H-11, merged
T: code review
B: none
[8:50 AM] Tia HR
Y: worked on IF-11
T: continue IF-11
B: none
[8:51 AM] Uma HR
Y: worked on H-13
T: continue H-13
B: none
[8:52 AM] Val HR
Y: pairing on the carryover
T: code review
B: none
[8:53 AM] Wes HR
Y: pairing on the carryover
T: code review
B: none
[8:54 AM] Xia HR
Y: pairing on the carryover
T: code review
B: none
[8:55 AM] Ann Logistics
Y: pairing on the carryover
T: code review
B: none
[8:56 AM] Bob Logistics
Y: pairing on the carryover
T: code review
B: none
[8:57 AM] Cy Logistics
Y: pairing on the carryover
T: code review
B: none
[8:58 AM] Dee Logistics
Y: worked on IF-3
T: continue IF-3
B: none
[8:59 AM] Yul Logistics
Y: pairing on the carryover
T: code review
B: none
[9:00 AM] Zed Logistics
Y: pairing on the carryover
T: code review
B: none
[9:01 AM] Eve Production
Y: finished P-311, merged
T: code review
B: none
[9:02 AM] Fay Production
Y: finished IF-13, merged
T: code review
B: none
[9:03 AM] Gus Production
Y: pairing on the carryover
T: code review
B: none
[9:04 AM] Hal Production
Y: pairing on the carryover
T: code review
B: none
[9:05 AM] Ida Production
Y: pairing on the carryover
T: code review
B: none
[9:06 AM] Jon Production
Y: finished IF-1, merged
T: code review
B: none
[9:07 AM] Kim Quality
Y: worked on IF-33
T: continue IF-33
B: none
[9:08 AM] Lou Quality
Y: pairing on the carryover
T: code review
B: none
[9:09 AM] Max Quality
Y: worked on IF-42
T: continue IF-42
B: none
[9:10 AM] Nia Quality
Y: pairing on the carryover
T: code review
B: none
[9:11 AM] Ola Quality
Y: pairing on the carryover
T: code review
B: none
[9:12 AM] Pat Quality
Y: pairing on the carryover
T: code review
B: none
[9:13 AM] Quinn Research
Y: pairing on the carryover
T: code review
B: none
[9:14 AM] Ray Research
Y: pairing on the carryover
T: code review
B: none
[9:15 AM] Sam Research
Y: pairing on the carryover
T: code review
B: none
[9:16 AM] Tia Research
Y: finished R-211, merged
T: code review
B: none
[9:17 AM] Uma Research
Y: worked on IF-15
T: continue IF-15
B: none
[9:18 AM] Val Research
Y: pairing on the carryover
T: code review
B: none
[9:19 AM] Ann Support
Y: pairing on the carryover
T: code review
B: none
[9:20 AM] Bob Support
Y: pairing on the carryover
T: code review
B: none
[9:21 AM] Wes Support
Y: worked on S-11
T: continue S-11
B: none
[9:22 AM] Xia Support
Y: pairing on the carryover
T: code review
B: none
[9:23 AM] Yul Support
Y: pairing on the carryover
T: code review
B: none
[9:24 AM] Zed Support
Y: pairing on the carryover
T: code review
B: none
[9:25 AM] Cy Testing
Y: worked on IF-27
T: continue IF-27
B: none
[9:26 AM] Dee Testing
Y: pairing on the carryover
T: code review
B: none
[9:27 AM] Eve Testing
Y: pairing on the carryover
T: code review
B: none
[9:28 AM] Fay Testing
Y: pairing on the carryover
T: code review
B: none
[9:29 AM] Gus Testing
Y: pairing on the carryover
T: code review
B: none
[9:30 AM] Hal Testing
Y: pairing on the carryover
T: code review
B: none

## Lint
Lint: who answered, what is missing, what to paste back
Reply: copy the Reply column into the chat. Suggest: copy Date..Note into the Log when it is right (never applied for you).
Name | Team | Lines | Y | T | B | Ids in T | Yours in T | Blocker | Done id | Flags | Reply | Date | ID | Verb | Note

## Log
Date | ID | Verb | Arg | Note | Check | State | Sprint | Into | Blk | Pts | Team | Burn
2026-09-23 | C-221 | commit | 1
2026-09-23 | IF-19 | commit | 1
2026-09-23 | IF-31 | commit | 1
2026-09-23 | IF-48 | commit | 1
2026-09-23 | IF-6 | commit | 1
2026-09-23 | E-221 | commit | 1
2026-09-23 | IF-21 | commit | 1
2026-09-23 | IF-22 | commit | 1
2026-09-23 | IF-23 | commit | 1
2026-09-23 | IF-24 | commit | 1
2026-09-23 | F-221 | commit | 1
2026-09-23 | IF-10 | commit | 1
2026-09-23 | IF-18 | commit | 1
2026-09-23 | IF-29 | commit | 1
2026-09-23 | IF-32 | commit | 1
2026-09-23 | H-11 | commit | 1
2026-09-23 | H-12 | commit | 1
2026-09-23 | H-13 | commit | 1
2026-09-23 | H-211 | commit | 1
2026-09-23 | IF-11 | commit | 1
2026-09-23 | IF-12 | commit | 1
2026-09-23 | IF-20 | commit | 1
2026-09-23 | IF-3 | commit | 1
2026-09-23 | IF-39 | commit | 1
2026-09-23 | L-321 | commit | 1
2026-09-23 | IF-1 | commit | 1
2026-09-23 | IF-13 | commit | 1
2026-09-23 | IF-2 | commit | 1
2026-09-23 | IF-25 | commit | 1
2026-09-23 | P-311 | commit | 1
2026-09-23 | IF-14 | commit | 1
2026-09-23 | IF-33 | commit | 1
2026-09-23 | IF-34 | commit | 1
2026-09-23 | IF-42 | commit | 1
2026-09-23 | Q-321 | commit | 1
2026-09-23 | IF-15 | commit | 1
2026-09-23 | IF-36 | commit | 1
2026-09-23 | IF-45 | commit | 1
2026-09-23 | IF-7 | commit | 1
2026-09-23 | R-211 | commit | 1
2026-09-23 | IF-16 | commit | 1
2026-09-23 | S-11 | commit | 1
2026-09-23 | S-12 | commit | 1
2026-09-23 | S-13 | commit | 1
2026-09-23 | S-221 | commit | 1
2026-09-23 | IF-17 | commit | 1
2026-09-23 | IF-27 | commit | 1
2026-09-23 | IF-28 | commit | 1
2026-09-23 | IF-35 | commit | 1
2026-09-23 | T-221 | commit | 1
2026-09-25 | C-221 | done
2026-09-25 | IF-32 | done
2026-09-25 | L-321 | done
2026-09-25 | IF-1 | block |  | waiting on Contracting for the Spot Orders interface
2026-09-25 | IF-7 | done
2026-09-25 | IF-35 | done
2026-09-28 | IF-23 | done
2026-09-28 | IF-12 | done
2026-09-28 | IF-34 | done
2026-09-28 | S-221 | done
2026-09-29 | IF-6 | done
2026-09-29 | E-221 | hold |  | pulled onto the demo prep
2026-09-29 | IF-18 | done
2026-09-29 | IF-39 | done
2026-09-29 | IF-25 | done
2026-09-29 | IF-36 | done
2026-09-29 | S-13 | punt |  | too hard as written - needs a spike first
2026-09-29 | IF-28 | done
2026-09-30 | IF-19 | done
2026-09-30 | F-221 | done
2026-09-30 | H-211 | done
2026-09-30 | IF-1 | unblock
2026-09-30 | Q-321 | done
2026-09-30 | S-12 | done
2026-09-30 | T-221 | done
2026-10-01 | IF-21 | done
2026-10-01 | H-12 | done
2026-10-01 | H-13 | commit | 1
2026-10-01 | H-13 | est | 8
2026-10-01 | H-22211 | drop
2026-10-01 | IF-14 | done
2026-10-01 | IF-16 | done
2026-10-02 | IF-48 | done
2026-10-02 | IF-29 | done
2026-10-02 | IF-20 | done
2026-10-02 | IF-2 | done
2026-10-02 | IF-45 | done
2026-10-02 | IF-17 | done
2026-10-05 | IF-31 | done
2026-10-05 | E-221 | done
2026-10-05 | H-11 | done
2026-10-05 | IF-1 | done
2026-10-05 | IF-13 | done
2026-10-05 | P-311 | done
2026-10-05 | R-211 | done
2026-10-06 | IF-22 | carry | 2
2026-10-06 | IF-24 | done
2026-10-06 | IF-10 | carry | 2
2026-10-06 | H-13 | done
2026-10-06 | IF-11 | carry | 2
2026-10-06 | IF-3 | done
2026-10-06 | IF-33 | carry | 2
2026-10-06 | IF-42 | done
2026-10-06 | IF-15 | carry | 2
2026-10-06 | S-11 | done
2026-10-06 | IF-27 | done

## Items
ID | Title | Tome | Epic | Team | Owner | Points | Prio | Added | Pts | Cur team | Sprint | Blocked | State | Blocked since | Days blocked | Blocker | Carried | Punts | Done on | In sprint | Age | KeyTP | KeyWatch | KeyAcc
C-11 | Build Market Presence | C Contracting & Sales | C1 Develop Markets & Pipeline | Contracting | Ann Contracting | 5 | 1 | 2026-09-23
C-12 | Develop Channel & Team Relationships | C Contracting & Sales | C1 Develop Markets & Pipeline | Contracting | Bob Contracting | 5 | 1 | 2026-09-23
C-13 | Maintain Opportunity Pipeline | C Contracting & Sales | C1 Develop Markets & Pipeline | Contracting | Cy Contracting | 5 | 1 | 2026-09-23
C-21 | Scope Opportunity & Bid Decision | C Contracting & Sales | C2 Win Contracts | Contracting | Dee Contracting | 5 | 1 | 2026-09-23
C-221 | Define Solution & Supply Terms | C Contracting & Sales | C2 Win Contracts | Contracting | Eve Contracting | 3 | 2 | 2026-09-23
C-2221 | Estimate Costs & Margins | C Contracting & Sales | C2 Win Contracts | Contracting | Fay Contracting | 3 | 3 | 2026-09-23
C-22221 | Classify Products & Destinations | C Contracting & Sales | C2 Win Contracts | Contracting | Ann Contracting | 3 | 3 | 2026-09-23
C-222221 | Run Denied-Party Screening | C Contracting & Sales | C2 Win Contracts | Contracting | Bob Contracting | 3 | 3 | 2026-09-23
C-222222 | Verify End-Use & End-User Statements | C Contracting & Sales | C2 Win Contracts | Contracting | Cy Contracting | 3 | 3 | 2026-09-23
C-222223 | Assess Diversion Risk | C Contracting & Sales | C2 Win Contracts | Contracting | Dee Contracting | 3 | 3 | 2026-09-23
C-22223 | Determine License Needs & File | C Contracting & Sales | C2 Win Contracts | Contracting | Eve Contracting | 3 | 3 | 2026-09-23
C-2223 | Approve Pricing | C Contracting & Sales | C2 Win Contracts | Contracting | Fay Contracting | 3 | 3 | 2026-09-23
C-223 | Assemble & Submit Proposal | C Contracting & Sales | C2 Win Contracts | Contracting | Ann Contracting | 3 | 2 | 2026-09-23
C-23 | Negotiate & Close | C Contracting & Sales | C2 Win Contracts | Contracting | Bob Contracting | 5 | 1 | 2026-09-23
C-31 | Book Orders & Supply Schedules | C Contracting & Sales | C3 Manage Contract Fulfillment | Contracting | Cy Contracting | 5 | 1 | 2026-09-23
C-32 | Coordinate Deliveries & Billing | C Contracting & Sales | C3 Manage Contract Fulfillment | Contracting | Dee Contracting | 5 | 1 | 2026-09-23
C-33 | Forecast Demand & Renewals | C Contracting & Sales | C3 Manage Contract Fulfillment | Contracting | Eve Contracting | 5 | 1 | 2026-09-23
IF-6 | Interface: Strategic Plan from Executive to Contracting | E Executive & Strategy | E1 Set Direction | Contracting | Fay Contracting | 5 | 1 | 2026-09-23
IF-9 | Interface: Approved Budgets from Executive to Contracting | E Executive & Strategy | E2 Plan & Allocate | Contracting | Ann Contracting | 5 | 1 | 2026-09-23
IF-19 | Interface: Trade-Compliance Policy from Executive to Contracting | E Executive & Strategy | E4 Manage Risk & Compliance | Contracting | Bob Contracting | 5 | 1 | 2026-09-23
IF-31 | Interface: Shipment Confirmations from Logistics to Contracting | L Logistics & Shipping | L3 Ship Customer Orders | Contracting | Cy Contracting | 5 | 1 | 2026-09-23
IF-48 | Interface: Renewal & Upsell Signals from Support to Contracting | S Customer Support & Feedback | S3 Synthesize Feedback & Insights | Contracting | Dee Contracting | 5 | 1 | 2026-09-23
E-11 | Scan Market & Race Scene | E Executive & Strategy | E1 Set Direction | Executive | Gus Executive | 5 | 1 | 2026-09-23
E-12 | Set Product & Race Strategy | E Executive & Strategy | E1 Set Direction | Executive | Hal Executive | 5 | 1 | 2026-09-23
E-13 | Approve Portfolio Mandate | E Executive & Strategy | E1 Set Direction | Executive | Ida Executive | 5 | 1 | 2026-09-23
E-21 | Consolidate Demand & Capacity Outlook | E Executive & Strategy | E2 Plan & Allocate | Executive | Jon Executive | 5 | 1 | 2026-09-23
E-221 | Draft Product-Line Plans | E Executive & Strategy | E2 Plan & Allocate | Executive | Kim Executive | 3 | 2 | 2026-09-23
E-2221 | Project Revenue & Bookings | E Executive & Strategy | E2 Plan & Allocate | Executive | Lou Executive | 3 | 3 | 2026-09-23
E-22221 | Collect Budget Submissions | E Executive & Strategy | E2 Plan & Allocate | Executive | Gus Executive | 3 | 3 | 2026-09-23
E-222221 | Check Submissions Against Targets | E Executive & Strategy | E2 Plan & Allocate | Executive | Hal Executive | 3 | 3 | 2026-09-23
E-222222 | Resolve Variances With Departments | E Executive & Strategy | E2 Plan & Allocate | Executive | Ida Executive | 3 | 3 | 2026-09-23
E-222223 | Lock Consolidated Budget | E Executive & Strategy | E2 Plan & Allocate | Executive | Jon Executive | 3 | 3 | 2026-09-23
E-22223 | Prioritize Capex | E Executive & Strategy | E2 Plan & Allocate | Executive | Kim Executive | 3 | 3 | 2026-09-23
E-2223 | Assemble Financial Plan | E Executive & Strategy | E2 Plan & Allocate | Executive | Lou Executive | 3 | 3 | 2026-09-23
E-223 | Reconcile & Approve Plan | E Executive & Strategy | E2 Plan & Allocate | Executive | Gus Executive | 3 | 2 | 2026-09-23
E-23 | Issue Budgets & Targets | E Executive & Strategy | E2 Plan & Allocate | Executive | Hal Executive | 5 | 1 | 2026-09-23
E-31 | Compile Performance Review | E Executive & Strategy | E3 Govern Performance | Executive | Ida Executive | 5 | 1 | 2026-09-23
E-32 | Hold Business Reviews | E Executive & Strategy | E3 Govern Performance | Executive | Jon Executive | 5 | 1 | 2026-09-23
E-33 | Direct Corrective Action | E Executive & Strategy | E3 Govern Performance | Executive | Kim Executive | 5 | 1 | 2026-09-23
E-4 | Manage Risk & Compliance | E Executive & Strategy | E4 Manage Risk & Compliance | Executive | Lou Executive | 8 | 1 | 2026-09-23
IF-4 | Interface: Demand Forecast from Contracting to Executive | C Contracting & Sales | C3 Manage Contract Fulfillment | Executive | Gus Executive | 5 | 1 | 2026-09-23
IF-21 | Interface: Budget Policy from Finance to Executive | F Finance | F1 Plan & Steward Budgets | Executive | Hal Executive | 5 | 1 | 2026-09-23
IF-22 | Interface: Planning Calendar from Finance to Executive | F Finance | F1 Plan & Steward Budgets | Executive | Ida Executive | 5 | 1 | 2026-09-23
IF-23 | Interface: Department Budget Requests from Finance to Executive | F Finance | F1 Plan & Steward Budgets | Executive | Jon Executive | 5 | 1 | 2026-09-23
IF-24 | Interface: Financial Statements & KPIs from Finance to Executive | F Finance | F3 Close Books & Report | Executive | Kim Executive | 5 | 1 | 2026-09-23
F-11 | Issue Budget Policy & Calendar | F Finance | F1 Plan & Steward Budgets | Finance | Max Finance | 5 | 1 | 2026-09-23
F-12 | Consolidate Budget Requests | F Finance | F1 Plan & Steward Budgets | Finance | Nia Finance | 5 | 1 | 2026-09-23
F-13 | Monitor Budget Execution | F Finance | F1 Plan & Steward Budgets | Finance | Ola Finance | 5 | 1 | 2026-09-23
F-21 | Process Procure-to-Pay | F Finance | F2 Run Financial Operations | Finance | Pat Finance | 5 | 1 | 2026-09-23
F-221 | Invoice Customers | F Finance | F2 Run Financial Operations | Finance | Quinn Finance | 3 | 2 | 2026-09-23
F-2221 | Monitor Aging & Prioritize | F Finance | F2 Run Financial Operations | Finance | Ray Finance | 3 | 3 | 2026-09-23
F-22221 | Send Dunning Notices | F Finance | F2 Run Financial Operations | Finance | Max Finance | 3 | 3 | 2026-09-23
F-222221 | Assess Customer Credit Position | F Finance | F2 Run Financial Operations | Finance | Nia Finance | 3 | 3 | 2026-09-23
F-222222 | Structure Payment Plans | F Finance | F2 Run Financial Operations | Finance | Ola Finance | 3 | 3 | 2026-09-23
F-222223 | Document & Monitor Arrangements | F Finance | F2 Run Financial Operations | Finance | Pat Finance | 3 | 3 | 2026-09-23
F-22223 | Coordinate Credit Holds | F Finance | F2 Run Financial Operations | Finance | Quinn Finance | 3 | 3 | 2026-09-23
F-2223 | Resolve Disputes & Write-Offs | F Finance | F2 Run Financial Operations | Finance | Ray Finance | 3 | 3 | 2026-09-23
F-223 | Apply & Reconcile Cash | F Finance | F2 Run Financial Operations | Finance | Max Finance | 3 | 2 | 2026-09-23
F-23 | Run Payroll | F Finance | F2 Run Financial Operations | Finance | Nia Finance | 5 | 1 | 2026-09-23
F-31 | Close Ledgers | F Finance | F3 Close Books & Report | Finance | Ola Finance | 5 | 1 | 2026-09-23
F-32 | Consolidate & Analyze Results | F Finance | F3 Close Books & Report | Finance | Pat Finance | 5 | 1 | 2026-09-23
F-33 | Publish Statements & KPIs | F Finance | F3 Close Books & Report | Finance | Quinn Finance | 5 | 1 | 2026-09-23
IF-5 | Interface: Billing Milestones from Contracting to Finance | C Contracting & Sales | C3 Manage Contract Fulfillment | Finance | Ray Finance | 5 | 1 | 2026-09-23
IF-10 | Interface: Approved Budgets from Executive to Finance | E Executive & Strategy | E2 Plan & Allocate | Finance | Max Finance | 5 | 1 | 2026-09-23
IF-18 | Interface: Performance Targets from Executive to Finance | E Executive & Strategy | E2 Plan & Allocate | Finance | Nia Finance | 5 | 1 | 2026-09-23
IF-29 | Interface: Payroll Inputs from HR to Finance | H Human Resources | H3 Administer HR Operations | Finance | Ola Finance | 5 | 1 | 2026-09-23
IF-32 | Interface: Shipping & Freight Documents from Logistics to Finance | L Logistics & Shipping | L3 Ship Customer Orders | Finance | Pat Finance | 5 | 1 | 2026-09-23
H-11 | Plan Headcount & Skills | H Human Resources | H1 Plan Workforce & Organization | HR | Sam HR | 5 | 1 | 2026-09-23
H-12 | Design Organization & Roles | H Human Resources | H1 Plan Workforce & Organization | HR | Tia HR | 5 | 1 | 2026-09-23
H-13 | Set Compensation Structures | H Human Resources | H1 Plan Workforce & Organization | HR | Uma HR | 5 | 1 | 2026-09-23
H-211 | Source Candidates | H Human Resources | H2 Staff & Develop Workforce | HR | Val HR | 3 | 2 | 2026-09-23
H-212 | Interview & Select | H Human Resources | H2 Staff & Develop Workforce | HR | Wes HR | 3 | 2 | 2026-09-23
H-213 | Onboard New Hires | H Human Resources | H2 Staff & Develop Workforce | HR | Xia HR | 3 | 2 | 2026-09-23
H-221 | Maintain Training Curricula | H Human Resources | H2 Staff & Develop Workforce | HR | Sam HR | 3 | 2 | 2026-09-23
H-22211 | Deliver Skills Training | H Human Resources | H2 Staff & Develop Workforce | HR | Tia HR | 3 | 3 | 2026-09-23
H-222121 | Stage Assessment Stations | H Human Resources | H2 Staff & Develop Workforce | HR | Uma HR | 3 | 3 | 2026-09-23
H-222122 | Score Workmanship Samples | H Human Resources | H2 Staff & Develop Workforce | HR | Val HR | 3 | 3 | 2026-09-23
H-222123 | Adjudicate & Record Results | H Human Resources | H2 Staff & Develop Workforce | HR | Wes HR | 3 | 3 | 2026-09-23
H-22213 | Issue & Record Certifications | H Human Resources | H2 Staff & Develop Workforce | HR | Xia HR | 3 | 3 | 2026-09-23
H-2222 | Certify Test Pilots | H Human Resources | H2 Staff & Develop Workforce | HR | Sam HR | 3 | 3 | 2026-09-23
H-2223 | Certify Compliance & Export Handlers | H Human Resources | H2 Staff & Develop Workforce | HR | Tia HR | 3 | 3 | 2026-09-23
H-223 | Track Qualifications & Deploy Staff | H Human Resources | H2 Staff & Develop Workforce | HR | Uma HR | 3 | 2 | 2026-09-23
H-23 | Manage Performance & Retention | H Human Resources | H2 Staff & Develop Workforce | HR | Val HR | 5 | 1 | 2026-09-23
H-31 | Compile Payroll Inputs | H Human Resources | H3 Administer HR Operations | HR | Wes HR | 5 | 1 | 2026-09-23
H-32 | Administer Benefits & Records | H Human Resources | H3 Administer HR Operations | HR | Xia HR | 5 | 1 | 2026-09-23
H-33 | Ensure Labor & Safety Compliance | H Human Resources | H3 Administer HR Operations | HR | Sam HR | 5 | 1 | 2026-09-23
IF-11 | Interface: Approved Budgets from Executive to HR | E Executive & Strategy | E2 Plan & Allocate | HR | Tia HR | 5 | 1 | 2026-09-23
L-11 | Unload & Check Freight | L Logistics & Shipping | L1 Receive Inbound Freight | Logistics | Yul Logistics | 5 | 1 | 2026-09-23
L-12 | Clear Import Customs | L Logistics & Shipping | L1 Receive Inbound Freight | Logistics | Zed Logistics | 5 | 1 | 2026-09-23
L-13 | Deliver to Production Stores | L Logistics & Shipping | L1 Receive Inbound Freight | Logistics | Ann Logistics | 5 | 1 | 2026-09-23
L-21 | Put Away Released Stock | L Logistics & Shipping | L2 Warehouse Finished Goods | Logistics | Bob Logistics | 5 | 1 | 2026-09-23
L-22 | Count & Reconcile Inventory | L Logistics & Shipping | L2 Warehouse Finished Goods | Logistics | Cy Logistics | 5 | 1 | 2026-09-23
L-23 | Stage Orders for Shipment | L Logistics & Shipping | L2 Warehouse Finished Goods | Logistics | Dee Logistics | 5 | 1 | 2026-09-23
L-31 | Plan Shipments & Book Carriers | L Logistics & Shipping | L3 Ship Customer Orders | Logistics | Yul Logistics | 5 | 1 | 2026-09-23
L-321 | Pick & Pack Orders | L Logistics & Shipping | L3 Ship Customer Orders | Logistics | Zed Logistics | 3 | 2 | 2026-09-23
L-3221 | Prepare Commercial Invoice & Packing List | L Logistics & Shipping | L3 Ship Customer Orders | Logistics | Ann Logistics | 3 | 3 | 2026-09-23
L-32221 | Validate License & Screening Data | L Logistics & Shipping | L3 Ship Customer Orders | Logistics | Bob Logistics | 3 | 3 | 2026-09-23
L-322221 | Assemble Filing Data Set | L Logistics & Shipping | L3 Ship Customer Orders | Logistics | Cy Logistics | 3 | 3 | 2026-09-23
L-322222 | Transmit Export & Destination Filings | L Logistics & Shipping | L3 Ship Customer Orders | Logistics | Dee Logistics | 3 | 3 | 2026-09-23
L-322223 | Archive Filing Acknowledgments | L Logistics & Shipping | L3 Ship Customer Orders | Logistics | Yul Logistics | 3 | 3 | 2026-09-23
L-32223 | Resolve Filing Exceptions | L Logistics & Shipping | L3 Ship Customer Orders | Logistics | Zed Logistics | 3 | 3 | 2026-09-23
L-3223 | Compile Battery & Dangerous-Goods Docs | L Logistics & Shipping | L3 Ship Customer Orders | Logistics | Ann Logistics | 3 | 3 | 2026-09-23
L-323 | Tender to Carrier | L Logistics & Shipping | L3 Ship Customer Orders | Logistics | Bob Logistics | 3 | 2 | 2026-09-23
L-33 | Track & Confirm Delivery | L Logistics & Shipping | L3 Ship Customer Orders | Logistics | Cy Logistics | 5 | 1 | 2026-09-23
IF-3 | Interface: Delivery Orders from Contracting to Logistics | C Contracting & Sales | C3 Manage Contract Fulfillment | Logistics | Dee Logistics | 5 | 1 | 2026-09-23
IF-12 | Interface: Approved Budgets from Executive to Logistics | E Executive & Strategy | E2 Plan & Allocate | Logistics | Yul Logistics | 5 | 1 | 2026-09-23
IF-20 | Interface: Trade-Compliance Policy from Executive to Logistics | E Executive & Strategy | E4 Manage Risk & Compliance | Logistics | Zed Logistics | 5 | 1 | 2026-09-23
IF-39 | Interface: Released Products from Quality to Logistics | Q Quality Assurance | Q2 Inspect & Release Product | Logistics | Ann Logistics | 5 | 1 | 2026-09-23
P-11 | Build Master Schedule | P Production | P1 Plan Production | Production | Eve Production | 5 | 1 | 2026-09-23
P-12 | Plan Materials | P Production | P1 Plan Production | Production | Fay Production | 5 | 1 | 2026-09-23
P-13 | Release Work Orders | P Production | P1 Plan Production | Production | Gus Production | 5 | 1 | 2026-09-23
P-21 | Order Components | P Production | P2 Procure & Kit Materials | Production | Hal Production | 5 | 1 | 2026-09-23
P-22 | Receive & Stage Materials | P Production | P2 Procure & Kit Materials | Production | Ida Production | 5 | 1 | 2026-09-23
P-23 | Kit Jobs to Line | P Production | P2 Procure & Kit Materials | Production | Jon Production | 5 | 1 | 2026-09-23
P-311 | CNC-Cut Carbon Plates | P Production | P3 Build Products | Production | Eve Production | 3 | 2 | 2026-09-23
P-312 | Finish & Deburr Plates | P Production | P3 Build Products | Production | Fay Production | 3 | 2 | 2026-09-23
P-313 | Fit-Check & Bag Frame Sets | P Production | P3 Build Products | Production | Gus Production | 3 | 2 | 2026-09-23
P-3211 | Prepare Line & Programs | P Production | P3 Build Products | Production | Hal Production | 3 | 3 | 2026-09-23
P-321211 | Align Stencil & Load Paste | P Production | P3 Build Products | Production | Ida Production | 3 | 3 | 2026-09-23
P-321212 | Print Panel | P Production | P3 Build Products | Production | Jon Production | 3 | 3 | 2026-09-23
P-321213 | Verify Paste Deposition | P Production | P3 Build Products | Production | Eve Production | 3 | 3 | 2026-09-23
P-32122 | Place Components | P Production | P3 Build Products | Production | Fay Production | 3 | 3 | 2026-09-23
P-32123 | Reflow Solder | P Production | P3 Build Products | Production | Gus Production | 3 | 3 | 2026-09-23
P-3213 | Inspect Panels | P Production | P3 Build Products | Production | Hal Production | 3 | 3 | 2026-09-23
P-322 | Assemble Through-Hole & Connectors | P Production | P3 Build Products | Production | Ida Production | 3 | 2 | 2026-09-23
P-323 | Test & Rework Boards | P Production | P3 Build Products | Production | Jon Production | 3 | 2 | 2026-09-23
P-331 | Assemble Airframe | P Production | P3 Build Products | Production | Eve Production | 3 | 2 | 2026-09-23
P-332 | Install Electronics Stack | P Production | P3 Build Products | Production | Fay Production | 3 | 2 | 2026-09-23
P-333 | Close Out & Serialize | P Production | P3 Build Products | Production | Gus Production | 3 | 2 | 2026-09-23
P-34 | Flash & Configure Firmware | P Production | P3 Build Products | Production | Hal Production | 5 | 1 | 2026-09-23
P-4 | Support Manufacturing Engineering | P Production | P4 Support Manufacturing Engineering | Production | Ida Production | 8 | 1 | 2026-09-23
IF-1 | Interface: Spot Orders from Contracting to Production | C Contracting & Sales | C3 Manage Contract Fulfillment | Production | Jon Production | 5 | 1 | 2026-09-23
IF-2 | Interface: Continuous Supply Schedule from Contracting to Production | C Contracting & Sales | C3 Manage Contract Fulfillment | Production | Eve Production | 5 | 1 | 2026-09-23
IF-13 | Interface: Approved Budgets from Executive to Production | E Executive & Strategy | E2 Plan & Allocate | Production | Fay Production | 5 | 1 | 2026-09-23
IF-25 | Interface: Production Crew from HR to Production | H Human Resources | H2 Staff & Develop Workforce | Production | Gus Production | 5 | 1 | 2026-09-23
IF-26 | Interface: Staffed Production Workforce from HR to Production | H Human Resources | H2 Staff & Develop Workforce | Production | Hal Production | 5 | 1 | 2026-09-23
IF-30 | Interface: Inbound Component Deliveries from Logistics to Production | L Logistics & Shipping | L1 Receive Inbound Freight | Production | Ida Production | 5 | 1 | 2026-09-23
IF-38 | Interface: Approved Supplier List from Quality to Production | Q Quality Assurance | Q1 Maintain Quality System | Production | Jon Production | 5 | 1 | 2026-09-23
IF-40 | Interface: CAPA Directives from Quality to Production | Q Quality Assurance | Q3 Manage Nonconformance & CAPA | Production | Eve Production | 5 | 1 | 2026-09-23
IF-41 | Interface: Engineering Baseline from Research to Production | R Research & Development | R4 Release Engineering Baseline | Production | Fay Production | 5 | 1 | 2026-09-23
IF-44 | Interface: Firmware Release from Research to Production | R Research & Development | R4 Release Engineering Baseline | Production | Gus Production | 5 | 1 | 2026-09-23
IF-50 | Interface: Rework Units from Testing to Production | T Testing | T3 Disposition & Report | Production | Hal Production | 5 | 1 | 2026-09-23
IF-51 | Interface: Test Rejects from Testing to Production | T Testing | T3 Disposition & Report | Production | Ida Production | 5 | 1 | 2026-09-23
Q-11 | Maintain Procedures & Standards | Q Quality Assurance | Q1 Maintain Quality System | Quality | Kim Quality | 5 | 1 | 2026-09-23
Q-12 | Author Acceptance & Inspection Criteria | Q Quality Assurance | Q1 Maintain Quality System | Quality | Lou Quality | 5 | 1 | 2026-09-23
Q-13 | Qualify & Audit Suppliers | Q Quality Assurance | Q1 Maintain Quality System | Quality | Max Quality | 5 | 1 | 2026-09-23
Q-21 | Inspect Units & Records | Q Quality Assurance | Q2 Inspect & Release Product | Quality | Nia Quality | 5 | 1 | 2026-09-23
Q-22 | Disposition Release Decisions | Q Quality Assurance | Q2 Inspect & Release Product | Quality | Ola Quality | 5 | 1 | 2026-09-23
Q-23 | Certify & Release Products | Q Quality Assurance | Q2 Inspect & Release Product | Quality | Pat Quality | 5 | 1 | 2026-09-23
Q-31 | Log & Screen Quality Events | Q Quality Assurance | Q3 Manage Nonconformance & CAPA | Quality | Kim Quality | 5 | 1 | 2026-09-23
Q-321 | Contain & Segregate | Q Quality Assurance | Q3 Manage Nonconformance & CAPA | Quality | Lou Quality | 3 | 2 | 2026-09-23
Q-3221 | Reproduce Failure | Q Quality Assurance | Q3 Manage Nonconformance & CAPA | Quality | Max Quality | 3 | 3 | 2026-09-23
Q-32221 | Perform Visual & X-Ray Inspection | Q Quality Assurance | Q3 Manage Nonconformance & CAPA | Quality | Nia Quality | 3 | 3 | 2026-09-23
Q-322221 | Map Failing Nets | Q Quality Assurance | Q3 Manage Nonconformance & CAPA | Quality | Ola Quality | 3 | 3 | 2026-09-23
Q-322222 | Isolate Faulty Components | Q Quality Assurance | Q3 Manage Nonconformance & CAPA | Quality | Pat Quality | 3 | 3 | 2026-09-23
Q-322223 | Characterize Failure Mode | Q Quality Assurance | Q3 Manage Nonconformance & CAPA | Quality | Kim Quality | 3 | 3 | 2026-09-23
Q-32223 | Cross-Section & Materials Analysis | Q Quality Assurance | Q3 Manage Nonconformance & CAPA | Quality | Lou Quality | 3 | 3 | 2026-09-23
Q-3223 | Confirm Root Cause | Q Quality Assurance | Q3 Manage Nonconformance & CAPA | Quality | Max Quality | 3 | 3 | 2026-09-23
Q-323 | Define Corrective Actions | Q Quality Assurance | Q3 Manage Nonconformance & CAPA | Quality | Nia Quality | 3 | 2 | 2026-09-23
Q-33 | Track Effectiveness & Close | Q Quality Assurance | Q3 Manage Nonconformance & CAPA | Quality | Ola Quality | 5 | 1 | 2026-09-23
IF-14 | Interface: Approved Budgets from Executive to Quality | E Executive & Strategy | E2 Plan & Allocate | Quality | Pat Quality | 5 | 1 | 2026-09-23
IF-33 | Interface: Line Nonconformance Reports from Production to Quality | P Production | P3 Build Products | Quality | Kim Quality | 5 | 1 | 2026-09-23
IF-34 | Interface: Line Nonconformances from Production to Quality | P Production | P3 Build Products | Quality | Lou Quality | 5 | 1 | 2026-09-23
IF-42 | Interface: Engineering Baseline from Research to Quality | R Research & Development | R4 Release Engineering Baseline | Quality | Max Quality | 5 | 1 | 2026-09-23
IF-46 | Interface: Field Complaint Reports from Support to Quality | S Customer Support & Feedback | S3 Synthesize Feedback & Insights | Quality | Nia Quality | 5 | 1 | 2026-09-23
IF-47 | Interface: Field Complaints from Support to Quality | S Customer Support & Feedback | S3 Synthesize Feedback & Insights | Quality | Ola Quality | 5 | 1 | 2026-09-23
IF-49 | Interface: Accepted Drones from Testing to Quality | T Testing | T3 Disposition & Report | Quality | Pat Quality | 5 | 1 | 2026-09-23
IF-52 | Interface: Test Records from Testing to Quality | T Testing | T3 Disposition & Report | Quality | Kim Quality | 5 | 1 | 2026-09-23
R-11 | Gather Race-Team & Market Inputs | R Research & Development | R1 Define Product Requirements | Research | Quinn Research | 5 | 1 | 2026-09-23
R-12 | Write Product Requirements | R Research & Development | R1 Define Product Requirements | Research | Ray Research | 5 | 1 | 2026-09-23
R-13 | Baseline Requirements | R Research & Development | R1 Define Product Requirements | Research | Sam Research | 5 | 1 | 2026-09-23
R-211 | Model Frame Geometry | R Research & Development | R2 Develop Product Design | Research | Tia Research | 3 | 2 | 2026-09-23
R-212 | Analyze Structure & Aero | R Research & Development | R2 Develop Product Design | Research | Uma Research | 3 | 2 | 2026-09-23
R-213 | Prototype & Iterate Frame | R Research & Development | R2 Develop Product Design | Research | Val Research | 3 | 2 | 2026-09-23
R-221 | Architect Electronics Suite | R Research & Development | R2 Develop Product Design | Research | Quinn Research | 3 | 2 | 2026-09-23
R-2221 | Capture FC Schematic | R Research & Development | R2 Develop Product Design | Research | Ray Research | 3 | 3 | 2026-09-23
R-22221 | Place Components & Plan Stackup | R Research & Development | R2 Develop Product Design | Research | Sam Research | 3 | 3 | 2026-09-23
R-222221 | Route Power Stages | R Research & Development | R2 Develop Product Design | Research | Tia Research | 3 | 3 | 2026-09-23
R-222222 | Route High-Speed & RF Nets | R Research & Development | R2 Develop Product Design | Research | Uma Research | 3 | 3 | 2026-09-23
R-222223 | Tune & Clean Up Routing | R Research & Development | R2 Develop Product Design | Research | Val Research | 3 | 3 | 2026-09-23
R-22223 | Run DRC & Prepare Fab Package | R Research & Development | R2 Develop Product Design | Research | Quinn Research | 3 | 3 | 2026-09-23
R-2223 | Bring Up FC Prototype | R Research & Development | R2 Develop Product Design | Research | Ray Research | 3 | 3 | 2026-09-23
R-223 | Develop ESC & VTX Boards | R Research & Development | R2 Develop Product Design | Research | Sam Research | 3 | 2 | 2026-09-23
R-224 | Integrate Electronics Package | R Research & Development | R2 Develop Product Design | Research | Tia Research | 3 | 2 | 2026-09-23
R-231 | Define Firmware Architecture | R Research & Development | R2 Develop Product Design | Research | Uma Research | 3 | 2 | 2026-09-23
R-232 | Implement Flight & Config Code | R Research & Development | R2 Develop Product Design | Research | Val Research | 3 | 2 | 2026-09-23
R-233 | Bench-Validate Firmware | R Research & Development | R2 Develop Product Design | Research | Quinn Research | 3 | 2 | 2026-09-23
R-24 | Integrate Design Data | R Research & Development | R2 Develop Product Design | Research | Ray Research | 5 | 1 | 2026-09-23
R-31 | Build Verification Units | R Research & Development | R3 Verify Design | Research | Sam Research | 5 | 1 | 2026-09-23
R-32 | Run Design Verification Tests | R Research & Development | R3 Verify Design | Research | Tia Research | 5 | 1 | 2026-09-23
R-33 | Disposition Findings | R Research & Development | R3 Verify Design | Research | Uma Research | 5 | 1 | 2026-09-23
R-41 | Compile Release Package | R Research & Development | R4 Release Engineering Baseline | Research | Val Research | 5 | 1 | 2026-09-23
R-42 | Review & Approve Release | R Research & Development | R4 Release Engineering Baseline | Research | Quinn Research | 5 | 1 | 2026-09-23
R-43 | Publish Baseline | R Research & Development | R4 Release Engineering Baseline | Research | Ray Research | 5 | 1 | 2026-09-23
IF-7 | Interface: Strategic Plan from Executive to Research | E Executive & Strategy | E1 Set Direction | Research | Sam Research | 5 | 1 | 2026-09-23
IF-8 | Interface: Portfolio Mandate from Executive to Research | E Executive & Strategy | E1 Set Direction | Research | Tia Research | 5 | 1 | 2026-09-23
IF-15 | Interface: Approved Budgets from Executive to Research | E Executive & Strategy | E2 Plan & Allocate | Research | Uma Research | 5 | 1 | 2026-09-23
IF-36 | Interface: Manufacturability Feedback from Production to Research | P Production | P4 Support Manufacturing Engineering | Research | Val Research | 5 | 1 | 2026-09-23
IF-45 | Interface: Customer Feedback from Support to Research | S Customer Support & Feedback | S3 Synthesize Feedback & Insights | Research | Quinn Research | 5 | 1 | 2026-09-23
S-11 | Run Help Desk & Community Channels | S Customer Support & Feedback | S1 Operate Support Channels | Support | Wes Support | 5 | 1 | 2026-09-23
S-12 | Publish Guides & Firmware Notes | S Customer Support & Feedback | S1 Operate Support Channels | Support | Xia Support | 5 | 1 | 2026-09-23
S-13 | Open Support Cases | S Customer Support & Feedback | S1 Operate Support Channels | Support | Yul Support | 5 | 1 | 2026-09-23
S-21 | Triage & Diagnose Cases | S Customer Support & Feedback | S2 Resolve Customer Cases | Support | Zed Support | 5 | 1 | 2026-09-23
S-221 | Authorize Returns | S Customer Support & Feedback | S2 Resolve Customer Cases | Support | Ann Support | 3 | 2 | 2026-09-23
S-2221 | Receive & Log Returns | S Customer Support & Feedback | S2 Resolve Customer Cases | Support | Bob Support | 3 | 3 | 2026-09-23
S-22221 | Diagnose Faults | S Customer Support & Feedback | S2 Resolve Customer Cases | Support | Wes Support | 3 | 3 | 2026-09-23
S-222221 | Replace Damaged Modules | S Customer Support & Feedback | S2 Resolve Customer Cases | Support | Xia Support | 3 | 3 | 2026-09-23
S-222222 | Rework Solder & Connectors | S Customer Support & Feedback | S2 Resolve Customer Cases | Support | Yul Support | 3 | 3 | 2026-09-23
S-222223 | Rebind & Configure Electronics | S Customer Support & Feedback | S2 Resolve Customer Cases | Support | Zed Support | 3 | 3 | 2026-09-23
S-22223 | Verify & Reflash Units | S Customer Support & Feedback | S2 Resolve Customer Cases | Support | Ann Support | 3 | 3 | 2026-09-23
S-2223 | QC & Restock or Scrap | S Customer Support & Feedback | S2 Resolve Customer Cases | Support | Bob Support | 3 | 3 | 2026-09-23
S-223 | Close RMAs & Ship Replacements | S Customer Support & Feedback | S2 Resolve Customer Cases | Support | Wes Support | 3 | 2 | 2026-09-23
S-23 | Close Cases & Follow Up | S Customer Support & Feedback | S2 Resolve Customer Cases | Support | Xia Support | 5 | 1 | 2026-09-23
S-31 | Mine Case & Telemetry Data | S Customer Support & Feedback | S3 Synthesize Feedback & Insights | Support | Yul Support | 5 | 1 | 2026-09-23
S-32 | Identify Product Issues & Trends | S Customer Support & Feedback | S3 Synthesize Feedback & Insights | Support | Zed Support | 5 | 1 | 2026-09-23
S-33 | Publish Feedback & Signals | S Customer Support & Feedback | S3 Synthesize Feedback & Insights | Support | Ann Support | 5 | 1 | 2026-09-23
IF-16 | Interface: Approved Budgets from Executive to Support | E Executive & Strategy | E2 Plan & Allocate | Support | Bob Support | 5 | 1 | 2026-09-23
T-11 | Author Test Procedures | T Testing | T1 Prepare Test Program | Testing | Cy Testing | 5 | 1 | 2026-09-23
T-12 | Plan Test Capacity & Schedule | T Testing | T1 Prepare Test Program | Testing | Dee Testing | 5 | 1 | 2026-09-23
T-13 | Maintain & Calibrate Rigs | T Testing | T1 Prepare Test Program | Testing | Eve Testing | 5 | 1 | 2026-09-23
T-21 | Bench-Test Units | T Testing | T2 Execute Acceptance Tests | Testing | Fay Testing | 5 | 1 | 2026-09-23
T-221 | Stage & Preflight Units | T Testing | T2 Execute Acceptance Tests | Testing | Gus Testing | 3 | 2 | 2026-09-23
T-2221 | Hover & Failsafe Checks | T Testing | T2 Execute Acceptance Tests | Testing | Hal Testing | 3 | 3 | 2026-09-23
T-22221 | Fly Speed Runs | T Testing | T2 Execute Acceptance Tests | Testing | Cy Testing | 3 | 3 | 2026-09-23
T-22222 | Fly Agility Circuits | T Testing | T2 Execute Acceptance Tests | Testing | Dee Testing | 3 | 3 | 2026-09-23
T-222231 | Extract Telemetry Metrics | T Testing | T2 Execute Acceptance Tests | Testing | Eve Testing | 3 | 3 | 2026-09-23
T-222232 | Compare Against Acceptance Gates | T Testing | T2 Execute Acceptance Tests | Testing | Fay Testing | 3 | 3 | 2026-09-23
T-222233 | Tag Pass-Fail & Archive Runs | T Testing | T2 Execute Acceptance Tests | Testing | Gus Testing | 3 | 3 | 2026-09-23
T-2223 | Consolidate Flight Results | T Testing | T2 Execute Acceptance Tests | Testing | Hal Testing | 3 | 3 | 2026-09-23
T-223 | Post-Flight Inspect & Return Units | T Testing | T2 Execute Acceptance Tests | Testing | Cy Testing | 3 | 2 | 2026-09-23
T-23 | Consolidate Test Data | T Testing | T2 Execute Acceptance Tests | Testing | Dee Testing | 5 | 1 | 2026-09-23
T-31 | Review Results & Disposition Units | T Testing | T3 Disposition & Report | Testing | Eve Testing | 5 | 1 | 2026-09-23
T-32 | Segregate Accepts & Rejects | T Testing | T3 Disposition & Report | Testing | Fay Testing | 5 | 1 | 2026-09-23
T-33 | Compile Test Records | T Testing | T3 Disposition & Report | Testing | Gus Testing | 5 | 1 | 2026-09-23
IF-17 | Interface: Approved Budgets from Executive to Testing | E Executive & Strategy | E2 Plan & Allocate | Testing | Hal Testing | 5 | 1 | 2026-09-23
IF-27 | Interface: Certified Test Pilots from HR to Testing | H Human Resources | H2 Staff & Develop Workforce | Testing | Cy Testing | 5 | 1 | 2026-09-23
IF-28 | Interface: Test Pilots from HR to Testing | H Human Resources | H2 Staff & Develop Workforce | Testing | Dee Testing | 5 | 1 | 2026-09-23
IF-35 | Interface: Configured Drones from Production to Testing | P Production | P3 Build Products | Testing | Eve Testing | 5 | 1 | 2026-09-23
IF-37 | Interface: Acceptance Test Procedure from Quality to Testing | Q Quality Assurance | Q1 Maintain Quality System | Testing | Fay Testing | 5 | 1 | 2026-09-23
IF-43 | Interface: Engineering Baseline from Research to Testing | R Research & Development | R4 Release Engineering Baseline | Testing | Gus Testing | 5 | 1 | 2026-09-23
M-1 | Enabler: telemetry data contract spike | A Architectural runway | A1 Enablers | HR | JC | 5 | 1 | 2026-10-01

## Teams
Team | Capacity | Committed | Done | Remaining | Pct done | Load | Blocked | Unassigned | Velocity | Backlog | Sprints of backlog | Flags | Type the teams and their capacity (points per sprint). Capacity drives Load.
Contracting | 24
Executive | 24
Finance | 24
HR | 24
Logistics | 24
Production | 24
Quality | 24
Research | 24
Support | 24
Testing | 24

## Roster
Name | Email | Team | Role | Org | In sprint | Open | Done | Blocked | Team share
Ann Contracting |  | Contracting
Ann Logistics |  | Logistics
Ann Support |  | Support
Bob Contracting |  | Contracting
Bob Logistics |  | Logistics
Bob Support |  | Support
Cy Contracting |  | Contracting
Cy Logistics |  | Logistics
Cy Testing |  | Testing
Dee Contracting |  | Contracting
Dee Logistics |  | Logistics
Dee Testing |  | Testing
Eve Contracting |  | Contracting
Eve Production |  | Production
Eve Testing |  | Testing
Fay Contracting |  | Contracting
Fay Production |  | Production
Fay Testing |  | Testing
Gus Executive |  | Executive
Gus Production |  | Production
Gus Testing |  | Testing
Hal Executive |  | Executive
Hal Production |  | Production
Hal Testing |  | Testing
Ida Executive |  | Executive
Ida Production |  | Production
JC |  | HR
Jon Executive |  | Executive
Jon Production |  | Production
Kim Executive |  | Executive
Kim Quality |  | Quality
Lou Executive |  | Executive
Lou Quality |  | Quality
Max Finance |  | Finance
Max Quality |  | Quality
Nia Finance |  | Finance
Nia Quality |  | Quality
Ola Finance |  | Finance
Ola Quality |  | Quality
Pat Finance |  | Finance
Pat Quality |  | Quality
Quinn Finance |  | Finance
Quinn Research |  | Research
Ray Finance |  | Finance
Ray Research |  | Research
Sam HR |  | HR
Sam Research |  | Research
Tia HR |  | HR
Tia Research |  | Research
Uma HR |  | HR
Uma Research |  | Research
Val HR |  | HR
Val Research |  | Research
Wes HR |  | HR
Wes Support |  | Support
Xia HR |  | HR
Xia Support |  | Support
Yul Logistics |  | Logistics
Yul Support |  | Support
Zed Logistics |  | Logistics
Zed Support |  | Support

## Epics
Epic | Tome | Target | Team | Points | Done | Pct done | Open | Blocked | ETA | Due | Status | KeyMS | Target is yours (a date the epic is promised by). ETA = remaining points / the team's 3-sprint velocity.
A1 Enablers | A Architectural runway
C1 Develop Markets & Pipeline | C Contracting & Sales
C2 Win Contracts | C Contracting & Sales
C3 Manage Contract Fulfillment | C Contracting & Sales
E1 Set Direction | E Executive & Strategy
E2 Plan & Allocate | E Executive & Strategy
E3 Govern Performance | E Executive & Strategy
E4 Manage Risk & Compliance | E Executive & Strategy
F1 Plan & Steward Budgets | F Finance
F2 Run Financial Operations | F Finance
F3 Close Books & Report | F Finance
H1 Plan Workforce & Organization | H Human Resources
H2 Staff & Develop Workforce | H Human Resources
H3 Administer HR Operations | H Human Resources
L1 Receive Inbound Freight | L Logistics & Shipping
L2 Warehouse Finished Goods | L Logistics & Shipping
L3 Ship Customer Orders | L Logistics & Shipping
P1 Plan Production | P Production
P2 Procure & Kit Materials | P Production
P3 Build Products | P Production
P4 Support Manufacturing Engineering | P Production
Q1 Maintain Quality System | Q Quality Assurance
Q2 Inspect & Release Product | Q Quality Assurance
Q3 Manage Nonconformance & CAPA | Q Quality Assurance
R1 Define Product Requirements | R Research & Development
R2 Develop Product Design | R Research & Development
R3 Verify Design | R Research & Development
R4 Release Engineering Baseline | R Research & Development
S1 Operate Support Channels | S Customer Support & Feedback
S2 Resolve Customer Cases | S Customer Support & Feedback
S3 Synthesize Feedback & Insights | S Customer Support & Feedback
T1 Prepare Test Program | T Testing
T2 Execute Acceptance Tests | T Testing
T3 Disposition & Report | T Testing

## Burndown
Burndown
Sprint (blank = current) |  |  | Sprint |  | Done
Team (blank = all) |  |  | Committed |  | Progress
Date | Day | Ideal | Remaining | Scope

## Velocity
Velocity and predictability
Team (blank = all)
Sprint | Starts | Committed | Done | Carried | Punted | Predictability | Carryover | Punt rate
Average done, last 3 finished sprints
The current sprint is the last row and is still running.