## Start
Agile kit -- Excel edition
Yellow cells are yours to type in. Everything else is a formula over the Items and Log tables. No macros.
Settings
Sprint 1 starts | 2026-10-17
Sprint length (calendar days) | 14
As of (blank = today)
Points unit | SP
Project
Stand-up date (blank = as of)
Now
Current sprint
Sprint starts
Sprint ends
Working day of sprint
As of
Thresholds (WORKFLOW section 6)
Blocked: amber after (days) | 3
Blocked: red after (days) | 5
Team load: high | 110%
Team load: low | 70%
Progress by working day 8 | 60%
Predictability: at least | 80%
Carryover: at most | 20%
Punt rate: at most | 20%
On-time delivery: at least | 80%
Same person, share of team points (bus factor) | 40%
Backlog age: flag after (days) | 90
Verbs (the Log table's third column)
Verb | Arg | State after | Meaning
commit | sprint N (blank = the sprint of the date) | OPEN | into a sprint at planning
carry | sprint N | OPEN | not done at sprint end: into the next sprint
done |  | DONE | finished, meets the Definition of Done
block |  |  | blocked from outside the team: why in Note (shows as WAIT)
unblock |  |  | the blocker is gone
hold |  | HOLD | interrupted by higher-priority work: why in Note
resume |  | OPEN | back from hold
punt |  | TODO | too hard as written: back to the team backlog, why in Note
redo | sprint N | OPEN | the demo found it wrong: back into a sprint
pass | team | TODO | another team should do it: into their backlog
drop |  | DROP | should not be done
est | points |  | re-estimate: the new size
sync | other ID |  | coordinated across teams (a note)
note |  |  | anything worth keeping
Every day
1. Townhall: copy the Teams meeting chat (Ctrl+A, Ctrl+C in the chat) and paste it into Standup!A6.
2. Lint: read the flags, copy the Reply column back into the chat, copy suggested rows (Date..Note) into the Log.
3. Log: type what happened -- one row per verb (done, block, hold, punt ...). Never edit old rows; add new ones.
4. Look: Quad (the weekly page), Health (thresholds), Teams, Burndown, Velocity. File > Print or paste into Outlook.
5. Dashboard: open agile-dashboard.html in Edge and load this file for charts you can copy into mail or slides.
Sprint planning: add Items, then a commit row per task. Sprint end: a carry row for each unfinished task.
The Items and Log tables grow when you type on the row just below them. Keep column order; add columns to the right.

## Quad
Sprint progress |  |  |  | On-time delivery
Technical priorities (this sprint) |  |  |  | Watch items (blocked, held, unassigned)
ID | State | Title | Owner | ID | State | Why | Days
30 / 60 / 90 milestones |  |  |  | Accomplishments (done in the last 7 days)
Epic | Status | Due | Pct done | ID | Done on | Title | Owner
Punted, last 4 sprints |  |  |  | Blocked > 3 days

## Health
Health: every metric against its threshold
RED and AMBER need an action; the action is in the last column (WORKFLOW section 6).
Metric | Value | Level | Action
Blocked past the red line (tasks) |  |  | Escalate to the PM today; name an owner for the outside dependency.
Blocked past the amber line (tasks) |  |  | Raise at the townhall; swarm or re-plan.
Teams over capacity |  |  | Move work out at the next refinement.
Teams under capacity |  |  | Pull ready work from the backlog.
Sprint progress (from working day 8) |  |  | Cut scope with the teams now, not on day 14.
Unassigned tasks in the sprint |  |  | Every committed task has one owner.
Predictability, last finished sprint |  |  | Commit to the 3-sprint velocity, not the hope.
Carryover, last finished sprint |  |  | Smaller tasks; split at refinement.
Punt rate, last finished sprint |  |  | The Definition of Ready is not holding: rewrite before planning.
Epics late or at risk |  |  | Re-plan the epic or move its target with the sponsor.
People over the bus-factor share |  |  | Pair or hand over; one person should not hold the team.
Backlog tasks older than the age limit |  |  | Refine or drop old backlog.
Silent at the last stand-up (people) |  |  | A 1:1 message; three days running is a conversation.
Log rows that do not check |  |  | Fix the ID or verb in the Log (Check column).

## Standup
Stand-up: paste the Teams chat into A6 (Ctrl+V). One line per row; Y: / T: / B: lines under each name.
Date
Names come from the Roster. "[8:31 AM] Ann Lee", "Ann Lee (08:31)" and "Ann Lee" on its own line all start a person.
Chat (paste here) | Name | Speaker | Tag | Text

## Lint
Lint: who answered, what is missing, what to paste back
Reply: copy the Reply column into the chat. Suggest: copy Date..Note into the Log when it is right (never applied for you).
Name | Team | Lines | Y | T | B | Ids in T | Yours in T | Blocker | Done id | Flags | Reply | Date | ID | Verb | Note

## Log
Date | ID | Verb | Arg | Note | Check | State | Sprint | Into | Blk | Pts | Team | Burn

## Items
ID | Title | Tome | Epic | Team | Owner | Points | Prio | Added | Pts | Cur team | Sprint | Blocked | State | Blocked since | Days blocked | Blocker | Carried | Punts | Done on | In sprint | Age | KeyTP | KeyWatch | KeyAcc

## Teams
Team | Capacity | Committed | Done | Remaining | Pct done | Load | Blocked | Unassigned | Velocity | Backlog | Sprints of backlog | Flags | Type the teams and their capacity (points per sprint). Capacity drives Load.

## Roster
Name | Email | Team | Role | Org | In sprint | Open | Done | Blocked | Team share

## Epics
Epic | Tome | Target | Team | Points | Done | Pct done | Open | Blocked | ETA | Due | Status | KeyMS | Target is yours (a date the epic is promised by). ETA = remaining points / the team's 3-sprint velocity.

## Burndown
Burndown
Sprint (blank = current) |  |  | Sprint |  | Done
Team (blank = all) |  |  | Committed |  | Progress
Date | Day | Ideal | Remaining | Scope

## Velocity
Velocity and predictability
Team (blank = all)
Sprint | Starts | Committed | Done | Carried | Punted | Predictability | Carryover | Punt rate
Average done, last 3 finished sprints
The current sprint is the last row and is still running.